## Read me
Compliance decisions register
What is still open, who decides it, and what it blocks
Last reviewed: 2026-10-02
Owner: [TO CONFIRM — a named person]
Status: SELF-ASSESSED. Not audited, not certified, not attested.
A to D are blockers: they unblock most of the rest. Take them in order.
F and G must be made TRUE before launch, not merely reviewed — both are already published on the site.
I expires: auditors sample a PAST period, so pull-request review has to start before you want the certificate, not when.
The public pages no longer show [TO CONFIRM] markers. Positions were written in as defensible defaults; this register is what a lawyer marks up.

## Decisions
Ref | Theme | Decision required | Who decides | Recommendation | Blocks | Priority | Status | Due
A | Applicable law | Which data-protection law the operator accepts as applying — CITRA, UAE PDPL, Saudi PDPL, GDPR, or a combination | Counsel | Draft to CITRA as the operative regime and GDPR as the ceiling. The addendum already follows the Article 28 pattern | Almost everything — vocabulary, breach clock, transfer rules, rights | BLOCKER | Open
B | Erasure | What happens when someone asks to be erased, given DELETE is revoked and nothing can be deleted | Counsel, then engineering | Both: rely on statutory retention where it applies; build a supervised redaction path (~2 weeks) for everything else | Every retention period in the ROPA | BLOCKER | Open
C | Operating model | Is a deployment operated by us, by the customer, or either — and who holds the cloud account | Commercial | Pick one as the default and price the other. Both are already built | Every infrastructure obligation in the terms | BLOCKER | Open
D | Hosting | Region, provider, encryption at rest, backup destination and retention | Commercial + engineering | Decide before any ministry-adjacent tender — this one can hard-stop a bid | Residency, encryption at rest, backups, 3 rows in the measures annex | BLOCKER | Open
E | Corporate identity | Registered entity name, legal form, commercial registration number, registered address | Operator | Mechanical. Blocks the most documents for the least effort | Privacy, DPA, Terms | High | Partly closed
F | Email addresses | privacy@cargosharks.com and security@cargosharks.com must exist | Operator | Create both. They are already published on the site and in security.txt | security.txt, privacy notice, DPA | High | MUST DO | Before launch
G | Incident lead | A named person owning the incident plan and the 24-hour breach commitment | Operator | Name one. An incident plan with no name produces a meeting, not a response | The published 24h breach commitment | High | MUST DO | Before launch
H | Fonts | Self-host the three typefaces instead of loading them from Google | Engineering | Do it. About an hour; removes a third-party disclosure of every visitor IP | Privacy notice section 04 | Medium | Open
I | Change management | Require pull-request review, starting now | Engineering | Start now if any certificate is ever wanted — auditors sample a PAST period and evidence cannot be created retrospectively | SOC 2 CC8.1, ISO A.8.32 | High | Open | Start now
J | Penetration test | Commission one | Operator | The highest-value purchase available. $5-15k, 2-4 weeks | CAIQ TVM-03; every framework | High | Open
K | Monitoring | Register an OpenTelemetry exporter and set up alerting | Engineering | NFR-18 requires it at handover. Currently wired with no exporter | CAIQ LOG-04 | Medium | Open
L | Audit search/export | Build the screen that searches and exports the audit log | Engineering | NFR-10 requires 12 months searchable AND exportable. Data is there; the screen is not | CAIQ LOG-05, DSP-08 | Medium | Open
M | TLS to database | Require TLS on the database connection | Engineering | Set sslmode in the connection string, or document the private-network boundary as the control | CAIQ CEK-01 | Medium | Open
N | Commercial terms | Fees, term, service levels, RPO/RTO, liability cap, governing law, insurance | Commercial + counsel | All deferred to the signed agreement on the public pages. Item: liability cap is what a customer legal team reaches for first | The signed agreement | High | Deferred